## DBDesign
Date | Time | Work | Number of present of member | Absent member
2020-11-03 | 8:00PM to 9:30PM | Problem statement Discussion | 4 | 0
2020-11-04 | 8:00PM to 9:00PM | Problem statement Understanding and DB design | 4 | 0
2020-11-05 | 7:30AM tp 8:45AM | Problem statement Understanding and DB design | 4 | 0
2020-11-06 | 8:00PM to 9:00PM | Problem statement Understanding and DB design | 4 | 0
2020-11-07 | 8:00PM to 10:00PM | Improvement in DB design based on Mam suggetions | 4 | 0
2020-11-08 | 1:00PM to 3:00PM | Finalizing DB Design and Store Procedure work Understanding | 4 | 0
2020-11-09 | 8:00PM to 9:30PM | Updating DB design as per suggessions and Registration & login page | 4 | 0
2020-11-10 | 8:00PM to 9:30PM | Final DB Design & Store Procedure Descussion, Registration & login page problem discussion | 4 | 0
2020-11-11 | 8:00PM to 9:30PM | DB change and Registration & login page validation | 4 | 0
2020-11-12 | 8:00PM to 9:30PM | DB change and Registration & login page validation | 4 | 0
2020-11-13 | 8:00PM to 9:30PM | DB change and Registration & login page validation | 4 | 0
2020-11-14 | 1:00PM to 3:00PM | farmer crop sell Request module discussion | 4 | 0
2020-11-15 | 2:00PM to 4:00PM | farmer crop sell Request module discussion and work Division | 4 | 0
2020-11-16 | 6:00PM to 9:00PM | farmer sell request module problem discussion | 4 | 0
2020-11-17 | 8:00PM to 9:30PM | farmer sell request module integration | 4 | 0
2020-11-18 | 8:00PM to 9:00PM | farmer sell request module integration and improvements | 4 | 0
2020-11-19 | 8:00PM to 10:30PM | farmer sell request module improvements as per Madam suggessions,Bidder Module Started | 4 | 0
2020-11-20 | 8:30AM to 8:30PM | Bidder Module improvement AS per madam suggetions | 3 | mansvini
2020-11-21 | 8:30AM to 8:30PM | working on Sold History Module,completed Sold History Module, | 3 | mansvini
2020-11-22 | 5:30PM to 8:30PM | Started working on View Market Place | 4 | 0
2020-11-23 | 8:30AM to 8:30PM | completed View Market Place Module, Started working on Farmer register Module | 4 | 0
2020-11-24 | 8:30AM to 8:30PM | Farmer Register Module Completed,Bidder Register module completed | 4 | 0
2020-11-25 | 8:30AM to 8:30PM | Sending Email integration Completed | 4 | 0
2020-11-26 | 8:30AM to 8:30PM | Admin Farmer register Approval completed | 4 | 0
2020-11-27 | 8:30AM to 8:30PM | Admin Bidder register Approval completed,Admin Claim Approval completed | 4 | 0
2020-11-28 | 8:30AM to 8:30PM | Admin Bid Approval completed,Admin Sell request Approval completed | 4 | 0
2020-11-29 | 8:30AM to 8:30PM | Login Integartion,Responsive Webpage work completed | 4 | 0

## Checklist
|  | To do | CheckList completed
Farmer registration |  | y | y
Bidder registration |  | y | y
Sold history |  | y | y
Market Place |  | y | y
Farmer Crop sell |  | y | y
Bidder Bidding |  | y | y
Farmer Insurace registration |  | y | y
farmer Insurance claim |  | y | y
Forgot Password Email Send |  | y | y
Admin Module | Farmer Register Approval | y | y
| Farmer Crop sell Request Approval | y | y
| Farmer Claim Approval | y | y
| Bid Approval | y | y
| Bidder Register Approval | y | y